## Sheet2
MCI Project Weekly Time Sheet
Team | Group 14B | Student ID | a1874232 |  |  | Week starting: | week 2 | Team | Group 14B | Student ID | a1874232 |  |  | Week starting: | week 3 | Team | Group 14B | Student ID | a1874232 |  |  | Week starting: | week 4 | Team | Group 14B | Student ID | a1874232 |  |  | Week starting: | week 5 | Team | Group 14B | Student ID | a1874232 |  |  | Week starting: | week 6
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action | Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action | Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action | Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action | Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 4/3/2024 | 18:00 | 21:00 | 3 | Prepare to meet the client for the first time | Clarify the main goals of the project and prepare for project implementation | Discussion of overall project goals | Monday | 11/3/2024 | 13:00 | 16:00 | 3 | Prepare for the second client meeting | Web page appearance and functionality further defined | Determination of target customers and determination of customer needs | Monday | 18/3/2024 | 20:00 | 23:00 | 3 | Determine the project details and functions with the client, discuss and modify as a group | Add functionality | Modify prototype drawing | Monday | 25/3/2024 | 12:00 | 18:00 | 6 | Learn to use git | Synchronization of team information and code | Feature discussion and details | Monday | 1/4/2024 | 23:00 | 2:00 | 3 | working on agenda | Ensure the effectiveness of the meeting | Understand preliminary website design drawings
Tuesday | 5/3/2024 | 16:00 | 18:00 | 2 | Discussion of overall project goals | Ensure project progress is consistent with client goals | Web service crowd research | Tuesday | 12/3/2024 | 12:00 | 15:00 | 3 | Determination of target customers and determination of customer needs | The functions required by customers are further revised and the early assumptions are changed. | Initial simple web page idea | Tuesday | 19/3/2024 | 11:00 | 13:00 | 2 | Modify prototype drawing | Add more guidance and obvious usage | Modify prototype drawing | Tuesday | 26/3/2024 | 23:00 | 1:00 | 2 | Feature discussion and details | Determine project details | Prototype drawing modification and discussion | Tuesday | 2/4/2024 | 13:00 | 16:00 | 3 | Understand preliminary website design drawings | Determined product development direction | Distribute work
Wednesday | 6/3/2024 | 16:00 | 20:00 | 4 | Web service crowd research | Further understanding of the project | Customer pain point research | Wednesday | 13/3/2024 | 16:00 | 19:00 | 3 | Initial simple web page idea | The web page is simply designed to show the client the earliest model to ensure that the project does not go in the wrong direction. | Initial simple web page idea | Wednesday | 20/3/2024 | 12:00 | 15:00 | 3 | Modify prototype drawing | Add more guidance and obvious usage | Further updates on project details | Wednesday | 27/3/2024 | 16:00 | 19:00 | 3 | Prototype drawing modification and discussion | Determine project details | Prototype drawing modification and discussion | Wednesday | 3/4/2024 | 18:00 | 21:00 | 3 | Distribute work | Ensure tasks are allocated effectively | discuss forum Coding
Thursday | 7/3/2024 | 16:00 | 20:00 | 4 | Customer pain point research | Ensure project functions meet customer needs | Project feasibility thinking | Thursday | 14/3/2024 | 12:00 | 16:00 | 4 | Initial simple web page idea | The web page is simply designed to show the client the earliest model to ensure that the project does not go in the wrong direction. | Data collection, looking for learning materials that are helpful to the project | Thursday | 21/3/2024 | 16:00 | 18:00 | 2 | Further updates on project details | Add functionality | Project synchronization and use of repo | Thursday | 28/3/2024 | 15:00 | 18:00 | 3 | Prototype drawing modification and discussion | Determine project details | feature design | Thursday | 4/4/2024 | 16:00 | 18:00 | 2 | discuss forum Coding | Provides a front-end web page for discussion | issue page Coding
Friday | 8/3/2024 | 18:00 | 21:00 | 3 | Project feasibility thinking | In order to achieve project feasibility | Technology stack discussion and personnel skills verification | Friday | 15/3/2024 | 15:00 | 19:00 | 4 | Data collection, looking for learning materials that are helpful to the project | Make project creation easier, share learning materials, and work as a team | Review CSS, HTML, JAVAscript and other knowledge | Friday | 22/3/2024 | 18:00 | 23:00 | 5 | Project synchronization and use of repo | Make sure you can use the repo to create projects to ensure that the project progress is not delayed | Project synchronization and use of repo | Friday | 29/3/2024 | 16:00 | 18:00 | 2 | feature design | Functional division and design allow each part of the project to be done by the right person | feature design | Friday | 5/4/2024 | 12:00 | 17:00 | 5 | issue page Coding | Designed issue page for instructor to use, functional development | general page Coding
Saturday | 9/3/2024 | 18:00 | 23:00 | 5 | Technology stack discussion and personnel skills verification | Ensure everyone’s skills are effectively utilized | Prepare for the second client meeting | Saturday | 16/3/2024 | 20:00 | 23:00 | 3 | Review CSS, HTML, JAVAscript and other knowledge | Review past knowledge and prepare for later code work | Determine the project details and functions with the client, discuss and modify as a group | Saturday | 23/3/2024 | 15:00 | 20:00 | 5 | Project synchronization and use of repo | Make sure you can use the repo to create projects to ensure that the project progress is not delayed | Learn to use git | Saturday | 30/3/2024 | 16:00 | 23:00 | 7 | feature design | Functional division and design allow each part of the project to be done by the right person | working on agenda | Saturday | 6/4/2024 | 18:00 | 22:00 | 4 | general page Coding | functional development | further upgrade
|  |  | Total | 21 | [6 empty] | Total | 20 | [6 empty] | Total | 20 | [6 empty] | Total | 23 | [6 empty] | Total | 20