## Sheet1
MCI Project Weekly Time Sheet
Team | Group 14B | Student ID: a1880840 |  |  |  | Week starting: | 28/02/2024
WEEK 1 | 28/02/2024 - 3/3/2024
Day | Date | a | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday
Tuesday
Wednesday | 28/02/2024 | 14:00 | 15:00 | 1 | Participate in group meeting to select project topic. | Ensure project aligns with team's interests and skills. | Send project preference email to instructor.
Thursday | 29/02/2024 | 19:00 | 23:00 | 4 | Analyze project requirements; Compile necessary documents and deadlines; Prepare agenda for first internal group meeting. | Gain a clear understanding of project scope and timeline to ensure smooth execution. | Create a comprehensive meeting agenda to guide discussions.
Friday | 01/03/2024 | 19:00 | 21:00 | 3 | Investigate suitable full-stack frameworks and database solutions for SaaS development. | Identify the most appropriate technology stack for the project's needs. | Conduct a comparative analysis of potential frameworks and tools.
Saturday | 02/03/2024 | 14:00 | 21:00 | 8 | Complete Angular crash course to gain foundational knowledge. | Acquire necessary skills to contribute effectively to project development. | Learn TypeScript and basic Angular concepts.
Sunday | 03/03/2024 | 14:00 | 21:00 | 8 | Continue Angular crash course to deepen understanding. | Strengthen proficiency in framework to facilitate coding tasks. | Explore Angular components and services.
|  |  | Total | 24
WEEK 2 | 04/03/2024 - 10/3/2024
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 04/03/2024 | 14:00 | 17:00 | 3 | Engage in first internal group meeting to review project deliverables, collaboration tools, and client meeting agenda. | Establish a shared understanding of project goals, milestones, and communication strategies; discuss project objectives and target audience. | Define communication and collaboration protocols; outline key points for first client meeting.
Tuesday | 05/03/2024 | 20:00 | 21:00 | 1 | Assist in drafting first client meeting agenda. | Ensure meeting agenda aligns with project objectives and client expectations. | Contribute to the development of a comprehensive meeting agenda.
Wednesday | 06/03/2024 | 18:00 | 19:00 | 1 | Participate in second internal group meeting to review and refine first meeting agenda draft. | Ensure alignment with upcoming pitch presentation milestone. | Collaborate to finalize the first client meeting agenda.
Thursday | 07/03/2024 | 19:00 | 20:00 | 1 | Assess first client meeting agenda to ensure readiness. | Prepare for a productive and informative client meeting. | Familiarize with the finalized first client meeting agenda.
Friday | 08/03/2024
Saturday | 09/03/2024 | 9:00 | 18:00 | 7 | Undertake Next.js crash course to expand framework knowledge. | Acquire skills in alternative framework to enhance project versatility. | Master Next.js fundamentals and component creation.
Sunday | 10/03/2024 | 10:00 | 19:00 | 7 | Deepen Next.js knowledge through continued crash course. | Strengthen proficiency in framework to support coding tasks. | Explore Next.js directives and lifecycle hooks.
|  |  | Total | 20
WEEK 3 | 11/03/2024 - 17/3/2024
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 11/03/2024 | 21:00 | 22:00 | 1 | Contribute to the development of pitch slides structure and template. | Ensure pitch slides align with the agreed-upon structure and content. | Develop a checklist for pitch slides components.
Tuesday | 12/03/2024 | 13:00 | 14:00 | 1 | Attend first client meeting to discuss project scope and key deliverables. | Establish a shared understanding of project objectives, target users, and core functionalities with the client. | Document clear project goals, target audience, and essential features.
Wednesday | 13/03/2024 | 15:00 | 17:00 | 2 | Engage in second internal meeting to plan pitch presentation. | Ensure progress aligns with upcoming pitch presentation milestone. | Create a prototype draft and assign pitch slide responsibilities.
Thursday | 14/03/2024 | 8:00 | 10:00 | 2 | Complete assigned sections of the pitch slides. | Contribute to the development of a comprehensive and persuasive pitch presentation. | Deliver assigned pitch slide sections.
Friday | 15/03/2024
Saturday | 16/03/2024 | 14:00 | 21:00 | 7 | Undertake MongoDB crash course to gain database proficiency. | Acquire necessary skills to design and manage the project's database. | Learn MongoDB fundamentals and basic queries.
Sunday | 17/03/2024 | 14:00 | 21:00 | 7 | Deepen MongoDB knowledge through continued crash course. | Enhance database management skills to optimize project performance. | Explore advanced MongoDB queries and optimization techniques.
|  |  | Total | 20
WEEK 4 | 18/03/2024 - 24/3/2024
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 18/03/2024 | 15:10 | 16:00 | 1 | Participate in second client meeting to present pitch slides and prototype. | Gather valuable feedback to refine pitch slides and prototype based on client input. | Document client feedback for pitch slides and prototype enhancements.
Tuesday | 19/03/2024 | 9:00 | 11:00 | 2 | Refine and proofread pitch slides to ensure quality. | Finalize pitch slides for Assignment 1 submission. | Deliver polished and error-free pitch slides.
Wednesday | 20/03/2024 | 14:00 | 15:00 | 1 | Engage in third internal group meeting to plan pitch presentation logistics. | Coordinate pitch presentation rehearsal and recording to meet Assignment 1 requirements. | Schedule pitch presentation rehearsal and recording sessions.
Thursday | 21/03/2025 | 9:00 | 12:00 | 3 | Complete crash course on authentication mechanisms. | Acquire knowledge of authentication best practices to secure the application. | Gain understanding of authentication concepts and implementation.
Friday | 22/03/2025 | 16:00 | 18:00 | 2 | Participate in pitch presentation rehearsal and recording. | Ensure readiness for Assignment 1 submission. | Deliver a polished and well-rehearsed pitch presentation recording.
Saturday | 23/03/2025 | 8:00 | 16:00 | 7 | Continue MongoDB crash course with focus on framework integration. | Acquire skills to seamlessly integrate the database with the chosen web framework. | Learn techniques for efficient MongoDB integration.
Sunday | 24/03/2026 | 18:00 | 23:00 | 5 | Assist in drafting business plan and third meeting agenda. | Ensure business plan and meeting agenda align with project objectives and next milestone. | Contribute to the development of a comprehensive business plan and meeting agenda.
|  |  | Total | 21
WEEK 5 | 25/03/2024 - 31/3/2024
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 25/03/2024 | 13:00 | 16:00 | 3 | Revise business plan incorporating client feedback. | Ensure business plan reflects client input and aligns with project goals. | Deliver an updated business plan that addresses client feedback.
Tuesday | 26/03/2024 | 9:00 | 14:00 | 4 | Undertake Bootstrap crash course to learn CSS framework. | Acquire skills in Bootstrap to enhance the application's user interface. | Learn Bootstrap fundamentals and component usage.
Wednesday | 27/03/2024
Thursday | 28/03/2024 | 9:00 | 14:00 | 5 | Continue Bootstrap crash course to deepen knowledge. | Strengthen proficiency in Bootstrap to create responsive and visually appealing layouts. | Explore Bootstrap grid system and utility classes.
Friday | 29/03/2024 | 16:00 | 18:00 | 2 | Participate in fourth internal group meeting to finalize business plan. | Ensure business plan is comprehensive and aligned with project objectives. | Collaborate to finalize the business plan for submission.
Saturday | 30/03/2024 | 8:00 | 10:00 | 2 | Engage in Q&A discussion to gather improvement ideas. | Identify potential enhancements to optimize the application. | Document ideas for future application improvements.
Sunday | 31/03/2024 | 18:00 | 23:00 | 5 | Explore Bootstrap custom components through continued crash course. | Acquire skills to create unique and interactive user interface elements. | Learn techniques for customizing Bootstrap components.
|  |  | Total | 21
WEEK 6 | 1/4/2024 - 7/4/2024
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 1/04/2024 | 10:00 | 18:00 | 8 | Initialize project repository and develop testing demo; Establish git collaboration guidelines. | Set up the foundation for collaborative development and ensure code quality. | Deliver functional main pages and testing demo.
Tuesday | 2/04/2024 | 9:00 | 12:00 | 3 | Participate in fifth internal group meeting to discuss repository management. | Define branching strategy and code collaboration practices to minimize conflicts. | Establish guidelines for effective teamwork and code integration.
Wednesday | 3/04/2024 | 8:00 | 10:00 | 2 | Attend fourth client meeting to gather feedback and suggestions. | Identify areas for improvement based on client input. | Document client feedback and prioritize enhancement tasks.
Thursday | 4/04/2024 | 9:00 | 11:00 | 2 | Draft minutes for the fourth client meeting. | Ensure accurate documentation of meeting discussions and action items. | Incorporate new enhancement requirements into project task list.
Friday | 5/04/2024 | 13:00 | 20:00 | 7 | Complete crash course on connecting front-end and back-end. | Acquire skills to enable seamless data exchange between application layers. | Learn techniques for efficient data management and communication.
Saturday | 6/04/2024
Sunday | 7/04/2024 | 17:00 | 23:00 | 6 | Continue crash course on front-end and back-end integration. | Strengthen proficiency in connecting application layers for optimal performance. | Explore API development and usage for data exchange.
|  |  | Total | 28
WEEK 7 | 8/4/2024 - 14/4/2024
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 8/04/2024 | 10:00 | 18:00 | 8 | Undertake crash course on filtering algorithms. | Acquire knowledge to implement robust filtering functionality in the application. | Learn techniques for efficient data filtering on the web.
Tuesday | 9/04/2024 | 10:00 | 12:00 | 4 | Complete crash course on search algorithms. | Gain skills to incorporate powerful search capabilities into the application. | Master search implementation techniques for web applications.
Wednesday | 10/04/2024 | 15:30 | 16:30 | 1 | Participate in fifth client meeting to gather feedback. | Identify areas for improvement based on client input. | Document client feedback and prioritize optimization tasks.
Thursday | 11/04/2024 | 9:00 | 12:00 | 3 | Undertake Express.js crash course to learn server-side framework. | Acquire skills to handle efficient data transfer between front-end and back-end. | Learn Express.js fundamentals and data handling techniques.
Friday | 12/04/2024
Saturday | 13/04/2024
Sunday | 14/04/2024
|  |  | Total | 16