## Sheet2
MCI Project Weekly Time Sheet
Team | Group 14B | Student ID | a1874232 |  |  | Week starting: | week 2 | Team | Group 14B | Student ID | a1874232 |  |  | Week starting: | week 3 | Team | Group 14B | Student ID | a1874232 |  |  | Week starting: | week 4 | Team | Group 14B | Student ID | a1874232 |  |  | Week starting: | week 5 | Team | Group 14B | Student ID | a1874232 |  |  | Week starting: | week 6
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action | Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action | Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action | Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action | Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 4/3/2024 | 18:00 | 21:00 | 3 | Prepare to meet the client for the first time | Clarify the main goals of the project and prepare for project implementation | Discussion of overall project goals | Monday | 11/3/2024 | 13:00 | 16:00 | 3 | Prepare for the second client meeting | Web page appearance and functionality further defined | Determination of target customers and determination of customer needs | Monday | 18/3/2024 | 20:00 | 23:00 | 3 | Determine the project details and functions with the client, discuss and modify as a group | Add functionality | Modify prototype drawing | Monday | 25/3/2024 | 12:00 | 18:00 | 6 | Learn to use git | Synchronization of team information and code | Feature discussion and details | Monday | 1/4/2024 | 23:00 | 2:00 | 3 | working on agenda | Ensure the effectiveness of the meeting | Understand preliminary website design drawings
Tuesday | 5/3/2024 | 16:00 | 18:00 | 2 | Discussion of overall project goals | Ensure project progress is consistent with client goals | Web service crowd research | Tuesday | 12/3/2024 | 12:00 | 15:00 | 3 | Determination of target customers and determination of customer needs | The functions required by customers are further revised and the early assumptions are changed. | Initial simple web page idea | Tuesday | 19/3/2024 | 11:00 | 13:00 | 2 | Modify prototype drawing | Add more guidance and obvious usage | Modify prototype drawing | Tuesday | 26/3/2024 | 23:00 | 1:00 | 2 | Feature discussion and details | Determine project details | Prototype drawing modification and discussion | Tuesday | 2/4/2024 | 13:00 | 16:00 | 3 | Understand preliminary website design drawings | Determined product development direction | Distribute work
Wednesday | 6/3/2024 | 16:00 | 20:00 | 4 | Web service crowd research | Further understanding of the project | Customer pain point research | Wednesday | 13/3/2024 | 16:00 | 19:00 | 3 | Initial simple web page idea | The web page is simply designed to show the client the earliest model to ensure that the project does not go in the wrong direction. | Initial simple web page idea | Wednesday | 20/3/2024 | 12:00 | 15:00 | 3 | Modify prototype drawing | Add more guidance and obvious usage | Further updates on project details | Wednesday | 27/3/2024 | 16:00 | 19:00 | 3 | Prototype drawing modification and discussion | Determine project details | Prototype drawing modification and discussion | Wednesday | 3/4/2024 | 18:00 | 21:00 | 3 | Distribute work | Ensure tasks are allocated effectively | discuss forum Coding
Thursday | 7/3/2024 | 16:00 | 20:00 | 4 | Customer pain point research | Ensure project functions meet customer needs | Project feasibility thinking | Thursday | 14/3/2024 | 12:00 | 16:00 | 4 | Initial simple web page idea | The web page is simply designed to show the client the earliest model to ensure that the project does not go in the wrong direction. | Data collection, looking for learning materials that are helpful to the project | Thursday | 21/3/2024 | 16:00 | 18:00 | 2 | Further updates on project details | Add functionality | Project synchronization and use of repo | Thursday | 28/3/2024 | 15:00 | 18:00 | 3 | Prototype drawing modification and discussion | Determine project details | feature design | Thursday | 4/4/2024 | 16:00 | 18:00 | 2 | discuss forum Coding | Provides a front-end web page for discussion | issue page Coding
Friday | 8/3/2024 | 18:00 | 21:00 | 3 | Project feasibility thinking | In order to achieve project feasibility | Technology stack discussion and personnel skills verification | Friday | 15/3/2024 | 15:00 | 19:00 | 4 | Data collection, looking for learning materials that are helpful to the project | Make project creation easier, share learning materials, and work as a team | Review CSS, HTML, JAVAscript and other knowledge | Friday | 22/3/2024 | 18:00 | 23:00 | 5 | Project synchronization and use of repo | Make sure you can use the repo to create projects to ensure that the project progress is not delayed | Project synchronization and use of repo | Friday | 29/3/2024 | 16:00 | 18:00 | 2 | feature design | Functional division and design allow each part of the project to be done by the right person | feature design | Friday | 5/4/2024 | 12:00 | 17:00 | 5 | issue page Coding | Designed issue page for instructor to use, functional development | general page Coding
Saturday | 9/3/2024 | 18:00 | 23:00 | 5 | Technology stack discussion and personnel skills verification | Ensure everyone’s skills are effectively utilized | Prepare for the second client meeting | Saturday | 16/3/2024 | 20:00 | 23:00 | 3 | Review CSS, HTML, JAVAscript and other knowledge | Review past knowledge and prepare for later code work | Determine the project details and functions with the client, discuss and modify as a group | Saturday | 23/3/2024 | 15:00 | 20:00 | 5 | Project synchronization and use of repo | Make sure you can use the repo to create projects to ensure that the project progress is not delayed | Learn to use git | Saturday | 30/3/2024 | 16:00 | 23:00 | 7 | feature design | Functional division and design allow each part of the project to be done by the right person | working on agenda | Saturday | 6/4/2024 | 18:00 | 22:00 | 4 | general page Coding | functional development | further upgrade
|  |  | Total | 21 | [6 empty] | Total | 20 | [6 empty] | Total | 20 | [6 empty] | Total | 23 | [6 empty] | Total | 20
Team | Group 14B | Student ID | a1874232 |  |  | Week starting: | week 7 | Team | Group 14B | Student ID | a1874232 |  |  | Week starting: | week 8 | Team | Group 14B | Student ID | a1874232 |  |  | Week starting: | week 9 | Team | Group 14B | Student ID | a1874232 |  |  | Week starting: | week 10 | Team | Group 14B | Student ID | a1874232 |  |  | Week starting: | week 11
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action | Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action | Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action | Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action | Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 22/4/2024 | 18:00 | 21:00 | 3 | Show the project content completed by Milestone 1 | Get the client's opinion on the project | Develop new plans based on project presentation results | Monday | 29/4/2024 | 18:00 | 21:00 | 3 | Prepare project presentations and collect user feedback | Demonstrating filter functionality and collecting feedback can make the project better | Change the next work plan based on customer feedback | Monday | 6/5/2024 | 18:00 | 21:00 | 3 | Front-end close add issue button design | Design button position and shape | Front-end close add issue button design | Monday | 13/5/2024 | 18:00 | 21:00 | 3 | Backend links to frontend | Connect the login and backend so that every Google user can use this website | Backend links to frontend | Monday | 20/5/2024 | 18:00 | 21:00 | 3 | Modify functional buttons and interfaces according to client requirements | After the meeting, we decided on the next direction to meet the client's requirements | Divide tasks according to requirements and ensure that tasks are assigned to each team member
Tuesday | 23/4/2024 | 13:00 | 18:00 | 5 | Develop new plans based on project presentation results | Create a task list based on the client's new opinions on the project and assign it to each team member | Creating a login interface | Tuesday | 30/4/2024 | 18:00 | 19:00 | 1 | Change the next work plan based on customer feedback | Modify the content according to the client's opinions to ensure that the project development direction meets the client's expectations | Demand determination and task division | Tuesday | 7/5/2024 | 16:00 | 18:00 | 2 | Front-end close add issue button design | Button built-in code writing | Prepare meeting agenda and presentation content | Tuesday | 14/5/2024 | 16:00 | 18:00 | 2 | Backend links to frontend | Connect the login and backend so that every Google user can use this website | Prepare meeting agenda and presentation content | Tuesday | 21/5/2024 | 16:00 | 18:00 | 2 | Divide tasks according to requirements and ensure that tasks are assigned to each team member | Assign tasks to each team member | Agenda and minutes
Wednesday | 24/4/2024 | 18:00 | 20:00 | 2 | Creating a login interface | Create a login interface to make the website look more professional | Connection login interface jump problem | Wednesday | 1/5/2024 | 18:00 | 20:00 | 2 | Demand determination and task division | Ensure that each team member has completed their tasks and resources are not wasted | Create accptance page and function. Currently not connected to the backend. Create the frontend page first.(admin only) | Wednesday | 8/5/2024 | 16:00 | 20:00 | 4 | Prepare meeting agenda and presentation content | Keep in line with customer expectations and gradually update the project | Front-end close general comment button design | Wednesday | 15/5/2024 | 16:00 | 20:00 | 4 | Prepare meeting agenda and presentation content | Keep in line with customer expectations and gradually update the project | New customer requirements are assigned to each team member | Wednesday | 22/5/2024 | 16:00 | 20:00 | 4 | Agenda and minutes | Record group discussions and teacher requirements, and decide what presentation results are needed for the next week | Front-end function modification, code writing
Thursday | 25/4/2024 | 16:00 | 20:00 | 4 | Connection login interface jump problem | The login interface jump design is as follows: admin will jump to admin, and user will jump to user. | Create client and administrator accounts using different accounts | Thursday | 2/5/2024 | 14:00 | 20:00 | 6 | Create accptance page and function. Currently not connected to the backend. Create the frontend page first.(admin only) | Distinguish between admin and user because they have different functions | Creating a discussion page (admin version) | Thursday | 9/5/2024 | 16:00 | 20:00 | 4 | Front-end close general comment button design | Design button position and shape | Front-end close general comment button design | Thursday | 16/5/2024 | 16:00 | 20:00 | 4 | New customer requirements are assigned to each team member | Modify content according to new requirements | Backend integration code writing | Thursday | 23/5/2024 | 16:00 | 20:00 | 4 | Front-end function modification, code writing | Modify the interface to fit various screens | Front-end function modification, code writing
Friday | 26/4/2024 | 16:00 | 21:00 | 5 | Create client and administrator accounts using different accounts | Design the account and password for admin login, admin will have additional functions. | Create a login method through Google API and change the login path | Friday | 3/5/2024 | 13:00 | 21:00 | 8 | Creating a discussion page (admin version) | Distinguish between admin and user because they have different functions | Change and edit the content of the acceptance page rejection | Friday | 10/5/2024 | 18:00 | 21:00 | 3 | Front-end close general comment button design | Button built-in code writing | Button Test | Friday | 17/5/2024 | 18:00 | 21:00 | 3 | Backend integration code writing | Try the backend connection of the functional button | Backend integration code writing | Friday | 24/5/2024 | 18:00 | 21:00 | 3 | Front-end function modification, code writing | Modify the interface to fit various screens | Comprehensively test the website to find bugs
Saturday | 27/4/2024 | 16:00 | 20:00 | 4 | Create a login method through Google API and change the login path | Users will log in with their Google account, saving registration time | Prepare project presentations and collect user feedback | Saturday | 4/5/2024 | 13:00 | 20:00 | 7 | Change and edit the content of the acceptance page rejection | Make returned content traceable | Front-end close add issue button design | Saturday | 11/5/2024 | 18:00 | 23:00 | 5 | Button Test | Test the usage of buttons in various situations | Backend links to frontend | Saturday | 18/5/2024 | 18:00 | 23:00 | 5 | Backend integration code writing | Try the backend connection of the functional button | Modify functional buttons and interfaces according to client requirements | Saturday | 25/5/2024 | 18:00 | 23:00 | 5 | Comprehensively test the website to find bugs | Check for bugs and improve website functionality | Comprehensively test the website to find bugs
|  |  | Total | 23 | [6 empty] | Total | 27 | [6 empty] | Total | 21 | [6 empty] | Total | 21 | [6 empty] | Total | 21
Team | Group 14B | Student ID | a1874232 |  |  | Week starting: | week 12
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 27/5/2024 | 18:00 | 21:00 | 3 | Debuging | Solve the bugs that may appear in the presentation | Debuging
Tuesday | 28/5/2024 | 12:00 | 18:00 | 6 | Debuging | Solve the bugs that may appear in the presentation | Prepare for presentation
Wednesday | 29/5/2024 | 13:00 | 19:00 | 6 | Prepare for presentation | Prepare the speech required for the presentation in advance and control the speaking time of each person | Prepare for presentation
Thursday | 30/5/2024 | 15:00 | 20:00 | 5 | Prepare for presentation | Prepare the speech required for the presentation in advance and control the speaking time of each person | Rehearsal presentation
Friday | 31/5/2024 | 16:00 | 21:00 | 5 | Rehearsal presentation | Ensure that every aspect of the project is running smoothly | Rehearsal presentation
Saturday | 1/6/2024 | 19:00 | 20:00 | 1 | Rehearsal presentation | Ensure that every aspect of the project is running smoothly | Rehearsal presentation
|  |  | Total | 26