## Sheet2
MCI Project Weekly Time Sheet
Team | 14B | Student ID | a1876131 |  |  | Week starting: | week 7
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 4.21 | 45440.6875 | 45440.7708 | 2 | Role allocation | group meeting | Finish up the individual tasks based on the group meeting
Tuesday | 4.22 | 35:00 | 39:00 | 4 | Fix the preexisting problems | Contribute to the website | Modify the sidebar and the code example list page
Friday | 4.25 | 38:00 | 46:00 | 8 | Learning API | Preparing for the back-end and front-end interaction | Understanding the basic concepts of the API and how front and back-end interaction
Saturday | 4.26 | 33:00 | 39:00 | 6 | Learning mongodb and try to make contribution to the project | Contribute to the development | Learn Mongodb and its different with other popular back end management framework
|  |  | Total | 20
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 4.28 | 34:00 | 39:00 | 5 | Contribute towards the first milestone report | Prepare for the milestone report | Finish the first milestone report
Tuesday | 4.29 | 35:00 | 39:00 | 4 | Group meeting | Sharing our thought enhance the coordination | Finalise the first milestone report, and discuss about the next stage of development
Wednesday | 4.3 | 44:00 | 46:00 | 2 | Watch more video on how to develop the website | Prepare for the development | Watching more example of how develop website with tailwind css and mongodb
Thursday | 4.31 | 37:00 | 39:00 | 2 | group meeting | group meeting | sharing some thoughts, concluding some main goals as well as share how to use git hub to collaborate
Friday | 5.01 | 38:00 | 41:00 | 3 | Contribute towards the backend framework | Prepare for website development | Add few lines, and understanding other people’s code
Saturday | 5.02 | 35:00 | 39:00 | 4 | Get myself fermilar with typescript and react | Prepare for website development | Build up the basic understanding of the framework react, and the concept of typescript
|  |  | Total | 20
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Wednesday | 5.06 | 33:00 | 38:00 | 5 | Contribute towards the API design and development | Prepare for website development | Finalise the post api files
Thursday | 5.07 | 37:00 | 40:00 | 3 | group meeting | enhance the group coordination | Clear everyone’s role and set up deadlines for the individual work
Friday | 5.08 | 38:00 | 44:00 | 6 | Learn testing concept and prepare for testing plan | preparing for the testing plan | View the files provided by the lecturer, read the article, learn mocha and browser stack
Saturday | 5.09 | 37:00 | 43:00 | 6 | Finish up the first version of the testing plan | preparing for the testing plan | Making use of mocha and browser stack to make the test, finish the unit test, and write the first version of the report
|  |  | Total | 20
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 5.11 | 40:00 | 42:00 | 2 | Group meeting about current stage | enhance the group coordination | Reporting on individuals stage so far, and discussed some details
Tuesday | 5.12 | 35:00 | 42:00 | 7 | Learn the basic concept of how to do the filter function | its important to make sure the objectives of the project is clear | Finish watch the video from YouTube and learned some basic concepts
Wednesday | 5.13 | 45440.6667 | 45440.7917 | 3 | Discuss about the feedback, finish up the group meeting minutes | Prepare for the client meeting | complete the meeting minutes and discussed about the expected deliverables next client meeting
Friday | 5.15 | 38:00 | 45440.5 | 10 | Developing the filter function | Develop the website | Adjusted the whole structure, try different method on achieve the filter function
Saturday | 5.16 | 45440.5833 | 39:00 | 1 | Try to develop the clear function in the sidebar | Continue on develop the website | Finish up the clear button, after click all the checked options got un-checked
|  |  | Total | 23
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 5.18 | 34:00 | 39:00 | 5 | Fixing the filter function and merged into develop branch | to be able to display the function for the client | Function can able to display during the client meeting, however,logical bugs still there,some tags are displayed as others
Tuesday | 5.19 | 35:00 | 39:00 | 4 | Writing meeting minutes and do the grammar check, post them online and send to the client | Correctly record client meeting | Done the client meeting, send to the client and post it on to the github
Wednesday | 5.2 | 32:00 | 34:00 | 2 | Filter bug fixing | All the tags displayed correctly | Tags bugs fixed, and in the filter, set different labels for the option, so that when click on others, not all the others options being selected
Thursday | 5.21 | 37:00 | 39:00 | 2 | group meeting | group meeting | discuss about how it goes with the bug fixing and the deliverable outcomes before next client meeting
Friday | 5.22 | 41:00 | 45440.5 | 7 | The close discussion Button being displayed in the code example page | Final bug fixing and project refinement | Correctly display the close discussion button, correctly handle discussion close function. after click jump back to the sample list page, add one more features “discuss_close” to all the code example in data base
Saturday | 5.23 | 24:00 | 37:00 | 1 | Preparing for the next meeting agenda | preparing for the next client meeting | Finalised the meeting agenda, and send to the client
|  |  | Total | 21
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 5.25 | 45448.7083 | 45448.7917 | 2 | Group role allocation | Group meeting | Discuss about when will the in-person meeting be hold, talk about what will be expected during the final presentation
Tuesday | 5.26 | 45448.5417 | 45448.6667 | 3 | Find out all the existing bugs and plan for the presentation | In-person group meeting | We Identify 11 fixable bugs, we has fix many gram marly issue, I will then be responsible to fix the accept approval and delete function, and many other roles.We decided what role each of us will play during the presentation
Wednesday | 5.27 | 32:00 | 45448 | 4 | Develop the deleting function | Develop the website | Change the api file, add one more condition to display all the result
Thursday | 5.28 | 37:00 | 39:00 | 2 | Modify the database | Prepare for the presentation | Prepare the data example we need for the final presentation
Friday | 5.29 | 41:00 | 45440.5 | 7 | Preparing for the final presentation | Prepare for the presentation | Writing the script, fix the bugs, practice for the presentation