## Sheet1
MCI Project Weekly Time Sheet
Team | Group 14B | Student ID: a1880840 |  |  |  | Week starting: | 28/02/2024
WEEK 1 | 28/02/2024 - 3/3/2024
Day | Date | a | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday
Tuesday
Wednesday | 28/02/2024 | 14:00 | 15:00 | 1 | Participate in group meeting to select project topic. | Ensure project aligns with team's interests and skills. | Send project preference email to instructor.
Thursday | 29/02/2024 | 19:00 | 23:00 | 4 | Analyse project requirements; Compile necessary documents and deadlines; Prepare agenda for first internal group meeting. | Gain a clear understanding of project scope and timeline to ensure smooth execution. | Create a comprehensive meeting agenda to guide discussions.
Friday | 01/03/2024 | 19:00 | 21:00 | 3 | Investigate suitable full-stack frameworks and database solutions for SaaS development. | Identify the most appropriate technology stack for the project's needs. | Conduct a comparative analysis of potential frameworks and tools.
Saturday | 02/03/2024 | 14:00 | 21:00 | 8 | Complete Angular crash course to gain foundational knowledge. | Acquire necessary skills to contribute effectively to project development. | Learn TypeScript and basic Angular concepts.
Sunday | 03/03/2024 | 14:00 | 21:00 | 8 | Continue Angular crash course to deepen understanding. | Strengthen proficiency in framework to facilitate coding tasks. | Explore Angular components and services.
|  |  | Total | 24
WEEK 2 | 04/03/2024 - 10/3/2024
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 04/03/2024 | 14:00 | 17:00 | 3 | Engage in first internal group meeting to review project deliverables, collaboration tools, and client meeting agenda. | Establish a shared understanding of project goals, milestones, and communication strategies; discuss project objectives and target audience. | Define communication and collaboration protocols; outline key points for first client meeting.
Tuesday | 05/03/2024 | 20:00 | 21:00 | 1 | Assist in drafting first client meeting agenda. | Ensure meeting agenda aligns with project objectives and client expectations. | Contribute to the development of a comprehensive meeting agenda.
Wednesday | 06/03/2024 | 18:00 | 19:00 | 1 | Participate in second internal group meeting to review and refine first meeting agenda draft. | Ensure alignment with upcoming pitch presentation milestone. | Collaborate to finalise the first client meeting agenda.
Thursday | 07/03/2024 | 19:00 | 20:00 | 1 | Assess first client meeting agenda to ensure readiness. | Prepare for a productive and informative client meeting. | Familiarise with the finalised first client meeting agenda.
Friday | 08/03/2024
Saturday | 09/03/2024 | 9:00 | 18:00 | 7 | Undertake Next.js crash course to expand framework knowledge. | Acquire skills in alternative framework to enhance project versatility. | Master Next.js fundamentals and component creation.
Sunday | 10/03/2024 | 10:00 | 19:00 | 7 | Deepen Next.js knowledge through continued crash course. | Strengthen proficiency in framework to support coding tasks. | Explore Next.js directives and lifecycle hooks.
|  |  | Total | 20
WEEK 3 | 11/03/2024 - 17/3/2024
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 11/03/2024 | 21:00 | 22:00 | 1 | Contribute to the development of pitch slides structure and template. | Ensure pitch slides align with the agreed-upon structure and content. | Develop a checklist for pitch slides components.
Tuesday | 12/03/2024 | 13:00 | 14:00 | 1 | Attend first client meeting to discuss project scope and key deliverables. | Establish a shared understanding of project objectives, target users, and core functionalities with the client. | Document clear project goals, target audience, and essential features.
Wednesday | 13/03/2024 | 15:00 | 17:00 | 2 | Engage in second internal meeting to plan pitch presentation. | Ensure progress aligns with upcoming pitch presentation milestone. | Create a prototype draft and assign pitch slide responsibilities.
Thursday | 14/03/2024 | 8:00 | 10:00 | 2 | Complete assigned sections of the pitch slides. | Contribute to the development of a comprehensive and persuasive pitch presentation. | Deliver assigned pitch slide sections.
Friday | 15/03/2024
Saturday | 16/03/2024 | 14:00 | 21:00 | 7 | Undertake MongoDB crash course to gain database proficiency. | Acquire necessary skills to design and manage the project's database. | Learn MongoDB fundamentals and basic queries.
Sunday | 17/03/2024 | 14:00 | 21:00 | 7 | Deepen MongoDB knowledge through continued crash course. | Enhance database management skills to optimise project performance. | Explore advanced MongoDB queries and optimisation techniques.
|  |  | Total | 20
WEEK 4 | 18/03/2024 - 24/3/2024
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 18/03/2024 | 15:10 | 16:00 | 1 | Participate in second client meeting to present pitch slides and prototype. | Gather valuable feedback to refine pitch slides and prototype based on client input. | Document client feedback for pitch slides and prototype enhancements.
Tuesday | 19/03/2024 | 9:00 | 11:00 | 2 | Refine and proofread pitch slides to ensure quality. | Finalise pitch slides for Assignment 1 submission. | Deliver polished and error-free pitch slides.
Wednesday | 20/03/2024 | 14:00 | 15:00 | 1 | Engage in third internal group meeting to plan pitch presentation logistics. | Coordinate pitch presentation rehearsal and recording to meet Assignment 1 requirements. | Schedule pitch presentation rehearsal and recording sessions.
Thursday | 21/03/2025 | 9:00 | 12:00 | 3 | Complete crash course on authentication mechanisms. | Acquire knowledge of authentication best practices to secure the application. | Gain understanding of authentication concepts and implementation.
Friday | 22/03/2025 | 16:00 | 18:00 | 2 | Participate in pitch presentation rehearsal and recording. | Ensure readiness for Assignment 1 submission. | Deliver a polished and well-rehearsed pitch presentation recording.
Saturday | 23/03/2025 | 8:00 | 16:00 | 7 | Continue MongoDB crash course with focus on framework integration. | Acquire skills to seamlessly integrate the database with the chosen web framework. | Learn techniques for efficient MongoDB integration.
Sunday | 24/03/2026 | 18:00 | 23:00 | 5 | Assist in drafting business plan and third meeting agenda. | Ensure business plan and meeting agenda align with project objectives and next milestone. | Contribute to the development of a comprehensive business plan and meeting agenda.
|  |  | Total | 21
WEEK 5 | 25/03/2024 - 31/3/2024
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 25/03/2024 | 13:00 | 16:00 | 3 | Revise business plan incorporating client feedback. | Ensure business plan reflects client input and aligns with project goals. | Deliver an updated business plan that addresses client feedback.
Tuesday | 26/03/2024 | 9:00 | 14:00 | 4 | Undertake Bootstrap crash course to learn CSS framework. | Acquire skills in Bootstrap to enhance the application's user interface. | Learn Bootstrap fundamentals and component usage.
Wednesday | 27/03/2024
Thursday | 28/03/2024 | 9:00 | 14:00 | 5 | Continue Bootstrap crash course to deepen knowledge. | Strengthen proficiency in Bootstrap to create responsive and visually appealing layouts. | Explore Bootstrap grid system and utility classes.
Friday | 29/03/2024 | 16:00 | 18:00 | 2 | Participate in fourth internal group meeting to finalise business plan. | Ensure business plan is comprehensive and aligned with project objectives. | Collaborate to finalise the business plan for submission.
Saturday | 30/03/2024 | 8:00 | 10:00 | 2 | Engage in Q&A discussion to gather improvement ideas. | Identify potential enhancements to optimise the application. | Document ideas for future application improvements.
Sunday | 31/03/2024 | 18:00 | 23:00 | 5 | Explore Bootstrap custom components through continued crash course. | Acquire skills to create unique and interactive user interface elements. | Learn techniques for customising Bootstrap components.
|  |  | Total | 21
WEEK 6 | 1/4/2024 - 7/4/2024
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 1/04/2024 | 10:00 | 18:00 | 8 | Initialise project repository and develop testing demo; Establish git collaboration guidelines. | Set up the foundation for collaborative development and ensure code quality. | Deliver functional main pages and testing demo.
Tuesday | 2/04/2024 | 9:00 | 12:00 | 3 | Participate in fifth internal group meeting to discuss repository management. | Define branching strategy and code collaboration practices to minimise conflicts. | Establish guidelines for effective teamwork and code integration.
Wednesday | 3/04/2024 | 8:00 | 10:00 | 2 | Attend fourth client meeting to gather feedback and suggestions. | Identify areas for improvement based on client input. | Document client feedback and prioritise enhancement tasks.
Thursday | 4/04/2024 | 9:00 | 11:00 | 2 | Draft minutes for the fourth client meeting. | Ensure accurate documentation of meeting discussions and action items. | Incorporate new enhancement requirements into project task list.
Friday | 5/04/2024 | 13:00 | 20:00 | 7 | Complete crash course on connecting front-end and back-end. | Acquire skills to enable seamless data exchange between application layers. | Learn techniques for efficient data management and communication.
Saturday | 6/04/2024
Sunday | 7/04/2024 | 17:00 | 23:00 | 6 | Continue crash course on front-end and back-end integration. | Strengthen proficiency in connecting application layers for optimal performance. | Explore API development and usage for data exchange.
|  |  | Total | 28
WEEK 7 | 8/4/2024 - 14/4/2024
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 8/04/2024 | 10:00 | 18:00 | 8 | Undertake crash course on filtering algorithms. | Acquire knowledge to implement robust filtering functionality in the application. | Learn techniques for efficient data filtering on the web.
Tuesday | 9/04/2024 | 10:00 | 12:00 | 4 | Complete crash course on search algorithms. | Gain skills to incorporate powerful search capabilities into the application. | Master search implementation techniques for web applications.
Wednesday | 10/04/2024 | 15:30 | 16:30 | 1 | Participate in fifth client meeting to gather feedback. | Identify areas for improvement based on client input. | Document client feedback and prioritise optimisation tasks.
Thursday | 11/04/2024 | 9:00 | 12:00 | 3 | Undertake Express.js crash course to learn server-side framework. | Acquire skills to handle efficient data transfer between front-end and back-end. | Learn Express.js fundamentals and data handling techniques.
Friday | 12/04/2024
Saturday | 13/04/2024
Sunday | 14/04/2024
|  |  | Total | 16
WEEK 8 | 15/4/2024 - 21/4/2024
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2024-04-15 | 10:00 | 18:00 | 8 | Implement basic filtering functionality in the application | Begin integration of filtering capabilities based on previous learnings. | Basic filtering functionality implemented.
Tuesday | 2024-04-16 | 10:00 | 12:00 | 4 | Test and debug filtering functionality. | Ensure filtering works as expected and identify any bugs. | Filtering functionality debugged and refined.
Wednesday | 2024-04-17 | 14:00 | 15:00 | 1 | Participate in sixth client meeting to present progress. | Get feedback on filtering implementation. | Feedback received and plan for next steps created.
Thursday | 2024-04-18 | 19:00 | 23:00 | 4 | Undertake Express.js crash course to learn server-side framework. | Acquire skills to handle efficient data transfer between front-end and back-end. | link front-end and back-end.
Friday | 2024-04-19 | 19:00 | 21:00 | 3 | Implement basic search functionality in the application. | Start adding search capabilities based on previous learnings | get the idea of add search
Saturday | 2024-04-20
Sunday | 2024-04-21 | 14:00 | 21:00 | 8 | Implement basic search functionality in the application. | Start adding search capabilities based on previous learnings | Basic search functionality implemented.
|  |  | Total | 28
WEEK 9 | 22/4/2024 - 28/4/2024
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2024-04-22 | 14:00 | 17:00 | 3 | Test and debug search functionality. | Ensure search works as expected and identify any bugs. | Search functionality debugged and refined.
Tuesday | 2024-04-23 | 9:00 | 18:00 | 7 | Conduct user testing with sample group. | Get real user feedback on search and filtering functionalities. | Collect and analyse feedback for improvements.
Wednesday | 2024-04-24 | 10:00 | 19:00 | 7 | Start implementing user feedback. | Improve functionalities based on user and client feedback. | Enhanced functionalities based on feedback.
Thursday | 2024-04-25 | 9:00 | 18:00 | 7 | Start implementing user feedback. | Improve functionalities based on user and client feedback. | Enhanced functionalities based on feedback.
Friday | 2024-04-26
Saturday | 2024-04-27
Sunday | 2024-04-28
|  |  | Total | 24
WEEK 10 | 29/4/2024 - 5/5/2024
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2024-04-29 | 10:00 | 18:00 | 8 | Participate in seventh client meeting to present progress. | Discuss user testing results and plan further enhancements. | Plan created based on client and user feedback.
Tuesday | 2024-04-30 | 10:00 | 14:00 | 4 | Implement advanced filtering and search options. | Enhance filtering and search functionalities for more robust use. | Advanced functionalities debugged and refined.
Wednesday | 2024-05-01 | 15:30 | 16:30 | 1 | Test advanced filtering and search functionalities. | Ensure advanced functionalities work as expected. | Feedback received and action plan created.
Thursday | 2024-05-02 | 9:00 | 12:00 | 3 | Refine and finalise advanced functionalities. | Polish the functionalities based on feedback. | Finalised advanced filtering and search options.
Friday | 2024-05-03
Saturday | 2024-05-04
Sunday | 2024-05-05
|  |  | Total | 16
WEEK 11 | 6/5/2024 - 12/5/2024
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2024-05-06 | 10:00 | 18:00 | 7 | Begin implementing discussion functionality. | Start adding discussion capabilities to the platform. | Basic discussion functionality implemented.
Tuesday | 2024-05-07 | 10:00 | 14:00 | 6 | Test and debug discussion functionality. | Ensure discussion features work as expected. | Discussion functionality debugged and refined.
Wednesday | 2024-05-08 | 15:30 | 16:30 | 7 | Test advanced filtering and search functionalities. | Ensure advanced functionalities work as expected. | Feedback received and action plan created.
Thursday | 2024-05-09 | 9:00 | 12:00 | 7 | Refine discussion functionality based on feedback. | Improve features based on client and user feedback. | Finalised discussion features.
Friday | 2024-05-10
Saturday | 2024-05-11
Sunday | 2024-05-12
|  |  | Total | 27
WEEK 12 | 13/5/2024 - 19/5/2024
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2024-05-13 | 10:00 | 18:00 | 8 | Begin implementation of the code sample review page for moderators. | Add functionality for moderators to approve or delete code submissions. | Basic review page implemented.
Tuesday | 2024-05-14 | 10:00 | 14:00 | 7 | Test and debug the review page functionality. | Ensure that the review functionalities work as expected and fix any issues. | Review page debugged and refined.
Wednesday | 2024-05-15 | 15:30 | 16:30 | 1 | Participate in ninth client meeting to gather feedback. | Present discussion functionality and gather feedback. | Feedback received and action plan created.
Thursday | 2024-05-16 | 9:00 | 12:00 | 8 | Refine and finalise the review page based on feedback. | Improve and finalise the review page for moderator use. | Finalised review page.
Friday | 2024-05-17 | 14:00 | 19:00 | 5 | Refine and finalise the review page based on feedback. | Improve and finalise the review page for moderator use. | Finalised review page.
Saturday | 2024-05-18
Sunday | 2024-05-19
|  |  | Total | 29
WEEK 13 | 20/5/2024 - 26/5/2024
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2024-05-20 | 15:30 | 16:30 | 1 | Participate in tenth client meeting to present the review page. | Gather feedback on the review functionalities from clients. | Feedback received and plan for enhancements created.
Tuesday | 2024-05-21 | 10:00 | 14:00 | 4 | Test and debug customisation and filtering functions. | Ensure the new functionalities work as expected and fix any issues. | Customisation and filtering functionalities debugged.
Wednesday | 2024-05-22 | 10:00 | 18:00 | 8 | Start implementing customisation and filtering functions. | Add functionality to allow users to customise levels, languages, and code types. | Basic customisation and filtering functionalities implemented.
Thursday | 2024-05-23 | 9:00 | 12:00 | 3 | Refine and finalise customisation and filtering features. | Improve features based on client feedback. | Finalised customisation and filtering features.
Friday | 2024-05-24 | 10:00 | 14:00 | 4 | Test and debug customisation and filtering functions. | Ensure the new functionalities work as expected and fix any issues. | Customisation and filtering functionalities debugged.
Saturday | 2024-05-25
Sunday | 2024-05-26
|  |  | Total | 19
WEEK14 | 27/5/2024 - 2/6/2024
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2024-05-27 | 15:30 | 16:30 | 1 | Participate in eleventh client meeting to showcase new features. | Gather client feedback on customisation and filtering functionalities. | Feedback received and plan for further improvements created.
Tuesday | 2024-05-28 | 10:00 | 14:00 | 4 | Test and debug the new features. | Ensure that the new features work as expected and fix any issues. | New features debugged and refined.
Wednesday | 2024-05-29 | 10:00 | 18:00 | 8 | Implement additional features based on feedback from previous meetings. | Enhance the platform with additional requested features. | Additional features implemented.
Thursday | 2024-05-30 | 9:00 | 12:00 | 3 | Make final adjustments and polish the platform. | Finalise all features and ensure the platform is ready for deployment. | Final adjustments made and platform polished.
Friday | 2024-05-31 | 10:00 | 18:00 | 8 | Demo presentation | Prepare the demo presentation script | 2 pages presentation script
Saturday | 2024-06-01 | 10:00 | 18:00 | 8 | Demo presentation | Prepare the demo presentation slides | slides prepared
Sunday | 2024-06-02
|  |  | Total | 31
WEEK 15 | 3/6/2024 - 9/6/2024 |  |  |  | Participate in twelfth client meeting to present the finalised features. | Get final feedback on all implemented functionalities. | Final feedback received and action plan for final tweaks created.
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2024-06-03 | 10:00 | 18:00 | 8 | Prepare my part for demo presentation | Practice the introduction and presentation flow | Practice the introduction and presentation flow
Tuesday | 2024-06-04 | 10:00 | 14:00 | 4 | Rehearsal for demo presentation with team group | Rehearsal for demo presentation with team group | Rehearsal for demo presentation with team group
Wednesday | 2024-06-05 | 13:30 | 16:30 | 3 | Demo presentation
Thursday | 2024-06-06 | 9:00 | 12:00 | 3 | Final report for the MICL project | Final report for the MICL project | Final report for the MICL project
Friday | 2024-06-07 | 10:00 | 14:00 | 4 | Final report for the MICL project | Final report for the MICL project | Final report for the MICL project
Saturday | 2024-06-08
Sunday | 2024-06-09
|  |  | Total | 22
|  |  | Total | 346